## Sheet1
# | Position | Track | Project | Assigned WON | # of Positions | RGS | Confirm / Tentative | Location | Requested On | Closed On | Onboarded On | Aging (days) | Time to Fulfillment | Status | Remarks
1 | MS Dynamics - Offshore | ADM | AX |  | 1 |  | Confirm | India | 2016-04-25 | 2016-04-29 |  | 117 | 5 | Closed | > Due to sudden exit of TribPub SME, replacement has been asked > Fulfilled and transition taken in 3 days and continued to support from 3rd May
2 | MS Dynamics - Onsite | ADM | AX |  | 1 |  | Confirm | Chicago/ India | 2016-05-12 | 2016-06-02 |  | 104 | 16 | Closed | 5/12: Requirements came initially for onsite. TCS suggested to fulfill it from offshore till long term replacement at Onsite 5/17: Saurabh's (offshore) CV provided 5/20: Feedback rejecting Saurabh 5/24: Shared Mansi's Profile, but not interviewed as she is mainly on AX2012 5/30: Shared Divya's (Offshore) Profile. In-parallel, TCS identified one associate for hiring at onsite and validation started 6/1: Interview of Divya by Sunil. Paul Mayle is using gmail, so he didn't get the invite and hence had to reschedule to 6/2
3 | .Net, UI resources with ADSS, AdIT | ADM | Engine |  | 2 |  | Confirm | India | 2016-05-17 | 2016-06-02 |  | 101 | 13 | Closed | 5/17: Requirements came 5/24: Biren's and Narayan's CV shared 5/27: Interview scheduled, but had to shift to 5/31 Pacific morning due to Chinmay's (TribPub) unavailability 5/31: Rescheduled again to Pacific night due to Chinmay's (TribPub) unavailability 5/31: Interview conducted on Pacific night, have asked Sunil to send the feedback at the earliest
4 | Mule ESB | ADM | TM |  | 1 |  | Confirm | India | 2016-06-02 | 2016-06-13 |  | 89 | 8 | Closed | 6/2: Requirements came 6/10: Interview scheduled 6/13: Confirmed (Sumanta Das)
5 | MS Dynamics - Onsite | ADM | CRM2011 |  | 1 |  | Tentative | Chicago | 2016-06-27 |  |  |  |  | Dropped | > Not a burning requirement, but good to have someone at onsite 8/5 - Profile of Vishnu Chilluru shared with Sunil. Pending confirmation from Sunil. 8/12 - No need for profile now at onsite
6 | QA - Functional | ADM | QA |  | 3 to 6 |  | Tentative | India | 2016-06-27 |  |  |  |  | Open | 08/05 - Tentative. May be needed in Sep'16
7 | Web Developers - FE | ADM | Digital |  | 3 |  | Tentative | India | 2016-06-27 |  |  |  |  | Open | 08/05 - Tentative. May be needed in Sep'16
8 | MS Dynamics CRM | ADM | CRM2011 |  | 1 |  | Confirm | India | 2016-07-13 | 2016-07-21 |  | 60 | 7 | Closed | 7/13: Requirements shared 7/19: Profile evaluated and confirmed, joining from 7/25
9 | Unix, Perl, PL/SQL | ADM | QA |  | ? |  | Tentative | India | 2016-06-27 |  |  |  |  | Open | 08/05 - Tentative. May be needed in Sep'16
10 | Business Analyst | ADM | TM |  | ? |  | Tentative | India | 2016-06-27 |  |  |  |  | Open | 08/05 - Tentative. May be needed in Sep'16
11 | QA - Dynamics AX | QA | QA |  | 1 |  | Confirm | India | 2016-06-29 | 2016-07-04 |  | 70 | 4 | Closed | 7/1: Profile shared with Sunil (Ritoban) 7/4: Confirmed and started from 7/5
12 | HTML, CSS, Kapow Scripting | ADM | Digital |  | 1 |  | Confirm | India | 2016-06-22 | 2016-08-02 |  | 75 | 30 | Closed | 08/05 : Ayan Mukherjee is confirmed from Content Lab
13 | MySQL DBA (Aurora) | Digital | Digital | 2707130 | 1 | 3833349 | Confirm | India | 2016-06-22 |  |  | 75 |  | Open | 08/05 : BA Identified. Pending confirmation from Arindam 08/16: Interview on 16th Aug, awaiting decision from tronc 08/31: Tronc confirmed that resource is not suitable. We need to find other resources 09/05: Looking into alternative profiles - none found till now. 09/09: Puja shared a BA resume - evaluation to be done
14 | QA for Xactly (Functional and Automation) | QA | QA |  | 2 |  | Confirm | India | 2016-07-25 | 2016-08-03 |  | 52 | 8 | Closed | 7/25: Requirements shared 7/27: 1 person (Subhas Jha) utilized from floor and confirmed 8/2: 2nd person (Simansu) shared and confirmed. To start from 8/8
15 | MS SSRS | ADM | TM |  | 1 |  | Confirm | India | 2016-08-03 | 2016-08-08 | 2016-08-25 | 45 | 4 | Closed | 8/3: Requirements shared 8/5 - Rashmi Gupta joined. To introduce to Sunil on 08/08
16 | .Net, UI resource (HTML5, CSS, Angular JS) | ADM | TM |  | 2 | 3832687 | Confirm | India | 2016-08-03 | 2016-08-11 | 2016-08-16 | 45 | 7 | Closed | 8/3: Requirements shared 8/5 - Avishek Sen is proposed. 8/8- Avishek Sen is rejected due to not having sufficient exp in AngularJS 8/9 - Joydeb proposed, interview on 8/11 8/11-Joydeb selected
17 | .Net | ADM | TM |  | 1 |  | Confirm | India | 2016-08-03 | 2016-08-12 | 2016-08-16 | 45 | 8 | Closed | 8/3: Requirements shared 8/12: Biswaroop proposed, interviewed and confirmed
18 | .Net | Internal | Web-Portal |  | 1 |  | Confirm | India | 2016-08-03 |  |  | 45 | -30418 | Open | 8/15: Realized need for a .NET experienced resource for web portal development 9/1: Still open, no resource identified as of now - Arti to continue
19 | LAMP Stack Developer | Digital | FSBO |  | 1 | 3830196 | Confirm | Lewisville, TX | 2016-08-12 | 2016-09-30 |  | 38 | 36 | Dropped | 8/15: Requirements for FISBO 8/22: One person was interviewed at onshore, but he does not have sufficient knowledge 8/26: Rakesh working with Samarjeet to get more profiles 09/05: 2 profiles at onsite shared. 09/12: No update - need to expedite as resources cannot be hold up 09/27: No update
20 | LAMP Stack Developer | Digital | FSBO |  | 4 | 3830248 | Confirm | India | 2016-08-12 | 2016-09-28 | 2016-10-03 | 38 | 34 | Closed | 8/15: Requirements for FISBO 8/26: Shared Rajashree's profile with customer, face to face BA interview to happen on 8/29. Judhajit's face to face BA interview to happen on 8/29. There is another BA, Rajsekhar kept on hold. Aother profile, (Pallava), internal with us - we will evaluate today 9/1: Pallava not suitable. There are 2 interviews for BA being held today. Asked Nilendu for other 2 profiles. 9/3: Rajashree not available. 9/5: To share 2 profiles (Rajesh and Sourav) on 9/6 9/8: Deepak Roy's resume shared 9/12: No update - need to expedite as resources cannot be hold up 9/27: Deepak Roy confirmed 9/28: Both Rajashree and Deepak Confirmed
21 | Essbase Developer | AMS | BackOffice |  | 1 | 3827468 | Confirm | Chicago or India | 2016-08-12 |  |  | 38 | -30425 | Dropped | 8/12: Need to hire a BA 8/26: BA interview in progress 9/1: Hiring approval obtained at offshore, proceeding for hiring as well 9/5: Roop conducting the interview for onshore BA 9/12: Interview in progress
22 | Peoplesoft Admin | AMS | BackOffice |  | 1 | 3831687 | Confirm | India | 2016-08-12 | 2016-09-09 | 2016-09-12 | 38 | 21 | Closed | 8/15: Requirements sent to Arnab-da 8/22: Shabbir confirmed 8/29: To get final confirmation for Shabbir today. Didn't get confirmation for Shabbir today 9/1: Shabbir was not confirmed, got another person, Abhijit who is Unix and Oracle DBA, can be groomed in the PS Admin job 9/9: Arijit joined the team
23 | Peoplesoft Technofunctional | AD | BackOffice | 2708127 | 2 | 3831679 | Confirm | India | 2016-08-12 |  |  | 38 | -30425 | Closed | 8/15: Requirements sent to Arnab-da 8/29: 2 more profiles from BBSR suggested, need to get progressz on those 9/1: Abhinav and Tejas's profile suggested, interview scheduled today. Tejas not joining Tribune, need to search for another profile 9/5: Abhinav confirmed, working with Shaym for other profile 9/12: No update yet on the second profile 9/21: Santosh Sahoo Confirmed
24 | Peoplesoft Technofunctional | AMS | BackOffice | 2708127 | 1 | 3834168 | Confirm | India | 2016-08-23 | 2016-08-30 |  | 31 | 6 | Closed | 8/23: Requirements sent to Arnab-da 8/26: Got one profile from Delhi (Kishore), evaluation in progress 8/29: Got one profile - Dhurjoy,he is coming over to GP on 08/30, will be confirmed tomorrow. 8/29: Dhurjoy's profile confirmed
25 | UI Developer | Internal | Web-Portal | 2707138 | 1 | 3833260 | Confirm | India | 2016-08-12 | 2016-08-22 | 2016-08-29 | 38 | 7 | Closed | 8/15: Realized need for an UI developer for web portal development 8/22: Uttorio Dutta confirmed (RGS: 3833260)
26 | Cyber Security Tester | IT IS |  |  | 1 | 3832779 | Confirm | India | 2016-08-19 |  |  | 33 | -30430 | Dropped | 8/19: Requirements came 8/26: Got one profile from ASU, evaluation in progress 9/1: Got one profile -Rocky Basak, internal evaluation in progress 9/2: Shared Rocky Basak's profile with Arindam 9/12: No update from Arindam about scheduling of the interview
27 | Network/FW, Load Balancer | IT IS | NetworkEOL | 2707130 | 1 | 3833357 | Confirm | India | 2016-08-19 |  |  | 33 | -30430 | Dropped | 8/19: Requirements came 9/1: No update 9/8: Proposed one GHD profile (Vivek Changela) to customer 9/12: No update
28 | AD (Active Dir), ADFS, 0365 | IT IS | AD Deforestation | 2707130 | 1 | 3833367 | Confirm | India | 2016-08-19 |  |  | 33 | -30430 | Dropped | 8/19: Requirements came 9/1: No update 9/12: Proposed Anujit's profile to customer
29 | .Net MVC | AD | Engine | 2707914 | 1 | 3833308 | Confirm | India | 2016-08-19 | 2016-08-31 |  | 33 | 9 | Closed | 8/19: Requirements came 8/22: Krishanu Sebastian Dhara is joining Tribune for .NET (RGS: 3833308) 8/26: Resume Shared 8/31: Krishanu confirmed with training requirements
30 | SQL BI-SSRS/SSAS/SSIS | AD | Adit/AX | 2707914 | 1 | 3833315 | Confirm | India | 2016-08-19 | 2016-08-25 | 2016-08-25 | 33 | 5 | Closed | 8/19: Requirements came 9/1: Rashmi is learning SSAS, tronc will start with low complexity work. Keeping this as "Proposed" still
31 | .Net MVC, AngularJS | AD | Adit 2.0 | 2707914 | 3 | 3833322 | Confirm | India | 2016-08-19 |  |  | 33 | -30430 | Proposed | 8/19: Requirements came 8/19: Resume shared with Kevin, interview not scheduled till 08/23 8/24: Interview of Suvankar happened 8/26: Suvankar failed interview, searching for more profiles 9/5: Still looking for 2 AngularJS and 1 .NET 9/19: Ajay confirmed 9/27: Proposed Rythm. Rhythm confired
32 | Plant Support | AMS | Manufacturing | 2708599 | 1 | 3831291 | Confirm | Chicago | 2016-08-19 | 2016-09-12 | 2016-09-12 | 33 | 17 | Closed | 8/19: This is position for Charlie's resignation 8/26: 2 candidates' interview happened, but not ok 9/1: No update, still looking for resources 9/5: No update, still looking for resources 9/12: Hired Ramana in Chicago
33 | AD Exchange | IT IS | ?? | 2707130 | 2 | 3833375 | Confirm | India | 2016-08-19 |  |  | 33 | -30430 | Dropped | 8/19: Requirements came 9/1: No update
34 | Automation Tester(Silenium) | QA | ADSS | 2707914 | 1 | 3833335 | Confirm | India | 2016-08-22 |  |  | 32 | -30431 | Closed | 8/22: For ADM 8/24: Proposed Rafal and had the interview, re-interview on Monday, 8/29 8/26: Failed interview, finding other profiles 9/5: Followed up with Anuradha for getting more profiles 9/12: Will get some profiles today. Sent profiles of Mukesh and Rashmi to Sunil/Mehrnaz 9/19: Rashmikant confirmed
35 | Functional Tester (with exp in DAM - Text, Photo, Graphics, PDF objects) | QA | East Coast DAM | 2707914 | 1 | 3834187 | Confirm | India | 2016-08-22 |  |  | 32 | -30431 | Open | 8/22: For ADM
36 | SQL BI-SSRS/SSAS/SSIS, .NET | AD | East Coast DAM | 2707138 | 1 | 3834197 | Confirm | India | 2016-08-23 |  |  | 31 | -30432 | Closed | 8/23: Requirements came 9/1: Got a profile from Unibet. Resource will be working as customer facing and will get the work done by the team 9/2: Kishen was a good candidate, but he needs immediate onsite, so that profile also not working out 9/12: No update, BA resumes are getting evaluated. Sent profile of Nipun patel 9/13: Nipun confirmed
37 | Unix, Perl, RestAPI | AD | East Coast DAM | 2707138 | 1 | 3834205 | Confirm | India | 2016-08-23 |  |  | 31 | -30432 | Proposed | 8/23: Requirements came 8/26: Satish is onboarded, he is learning Perl now, not placed with customer till now 9/19: Resume for Satish and Subhankar sent to customer 9/23: Alex asked some questions which were answered
38 | Unix, Perl, PosgreSQL | AD | Newsgate Upgrade | 2707137 | 1 | 3834209 | Confirm | Chicago/ India | 2016-08-23 |  |  | 31 | -30432 | Proposed | 8/23: Requirements came 8/26: Satish is onboarded, he is learning Perl now, not placed with customer till now 9/19: Resume for Satish and Subhankar sent to customer 9/23: Alex asked some questions which were answered
39 | Functional Tester (with exp in PDF file format/objects, fonts) | QA | Newsgate Upgrade | 2707137 | 1 | 3836305 | Confirm | Chicago/ India | 2016-08-23 |  |  | 31 | -30432 | Open | 8/22: Requirements came 8/25: Informed Arun about it- he is looking for profiles
40 | Informatica 8x,9x, Unix Shell scripting, MS-SQL tuning & optimization | AD | BackOffice - BI | 2708127 | 1 | 3836869 | Confirm | India | 2016-08-26 | 2016-09-06 | 2016-09-12 | 28 | 8 | Closed | 8/26: Requirements came 8/31: Balaram Ghosh proposed 9/5: Balaram's interview was good however failed and client wants to see more profiles. Have talked to Arindam, will release him on Wed, if Client is not agreeing to take him 9/6: Balaram confirmed
41 | Newsgate | AMS | Editorial | 2707138 | 1 | TBC | Confirm | India | 2016-08-22 |  |  | 32 | -30431 | Closed | 8/22: Tribune raised concern about Newsgate skillset 8/25: Amol and Sriraj interviewed by Tronc 8/26: Confirmed Amol,anshuman following up with Mansur to roll out the offer 9/1: Need to talk to Amol to check his availability for Kolkata 9/12: Amol confirmed - Mansur to talk to Amol today and confirm the joining
42 | HTML5, Bootstrap | Digital | FSBO | 2707138 | 2 | TBC | Confirm | India | 2016-08-31 |  |  | 25 | -30438 | Proposed | 8/31: Requirements came 9/1: Sent requirements for Sarani 9/5: Shared Aditi's and Suvankar's profile 09/12: No update - need to expedite as resources cannot be hold up 10/03: Resources may be needed, Arindam following up with Customer
43 | Agile Scrum Master (Certified) | Digital | FSBO | 2707138 | 1 | TBC | Confirm | India | 2016-09-03 |  |  | 22 | -30440 | Closed | 9/3: Requirements came 9/9: Proposed Nisha's resume 09/12: No update - need to expedite as resources cannot be hold up 09/30: Nisha selected
44 | Project Manager with Scrum experience (Offshore) | AD | PM-Pool | 2707138 | 1 | TBC | Confirm | India | 2016-09-23 |  |  | 8 | -30455 | Closed | 9/23: Requirements came 9/28: Avishek Sen confirmed
45 | Project Manager with Scrum experience (Onsite) | AD | PM-Pool | 2707137 | 1 | TBC | Confirm | Chicago | 2016-09-23 |  |  | 8 | -30455 | Closed | 9/23: Requirements came 9/28: Rakesh confirmed
46 | MS BI, SSAS, Informatica | AMS | Back Office | 2707137 | 1 | TBC | Confirm | Chicago | 2016-09-23 |  |  | 8 | -30455 | Open | 9/23: Requirements came 9/27: Profile evaluation going on for hiring
47 | Newsgate UI | AMS | Editorial | 2707137 | 1 | TBC | Confirm | Chicago | 2016-09-30 |  |  | 3 | -30460 | Open | 9/23: Requirements came 9/27: Profile evaluation going on for hiring
48 | Functional Tester | QA | Territory Management | 2707137 | 1 | TBC | Confirm | Chicago | 2016-09-30 |  |  | 3 | -30460 | Open | 9/23: Requirements came 9/27: Profile evaluation going on for hiring
49 | LAMP Stack Developer | Digital | FSBO |  | 3 | TBC | Confirm | India | 2016-10-03 |  |  | 2 | -30461 | Open | 10/3: Requirements came
50 | Functional Tester | Digital-QA | FSBO | 1 | 1 | TBC | Confirm | India | 2016-10-03 |  |  | 2 | -30460 | Open | 10/3: Requirements came
51 | Automation Tester(Silenium) | Digital-QA | FSBO | 1 | 1 | TBC | Confirm | India | 2016-10-03 |  |  | 2 | -30460 | Open | 10/3: Requirements came
52 | .NET MS SQL, SSIS | AD | East Coast DAM | 1 | 1 | TBC | Confirm | India | 2016-10-03 |  |  | 2 | -30460 | Open | 10/3: Requirements came
Formulas:
Aging (days) = NETWORKDAYS([Requested On],TODAY())
Time to Fulfillment = NETWORKDAYS([Requested On],[Closed On])